## Detail Report of Contracts new
|  |  |  | Contract Amount |  |  | Contract Duration |  |  | Expiry Date |  | Physical Accomplishment
REGION | PROJECT NAME | CONTRACT NUMBER / PACKAGE | DESCRIPTION | Original | Revised | Contractor Name | Original | Revised | Effectivity of Contract / NTP | Original | Revised | Target | Actual | Slippage | Billed Amount | Remarks
2020
REGION 1
Lower Agno RISIP,Pangasinan
|  | LARISIP-LARIS-029 | Construction of Trapezoidal Concrete Canal Lining and Appurtenant Structures (Sta. 0+009.00 - Sta. 2+310.00) of LARIS A-Extra, L = 2,286.00 m. | 13154283.69 |  | BFT CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 90.57 | 86.01 | -4.56 |  | ON-GOING
|  | LARISIP-LARIS-030 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 0+000.00 - Sta. 0+914.00) of LARIS Lateral B, L = 881.00 m. | 8935119 |  | BFT CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 90.57 | 100 | 9.43 |  | COMPLETED
|  | LARISIP-LARIS-031 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structure (Sta. 0+941.00 - Sta. 1+611.00) of LARIS Lateral B, L = 686.00 m. | 7279550 |  | FSB CONSTRUCTION INC. | 240 |  | 2020-03-09 | 2020-11-03 |  | 93.67 | 100 | 6.33 |  | COMPLETED
|  | LARISIP-LARIS-032 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 1+611.00 - Sta. 2+582.00) of LARIS Lateral B, L = 957.00 m. | 9997650 |  | ANGEL BUILDERS & CONSTRUCTION SUPPLY | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 100 | 8.17 |  | COMPLETED
|  | LARISIP-LARIS-033 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 2+582.00 - Sta. 3+926.00) of LARIS Lateral B, L = 1,321.00 m | 12092830 |  | ANGEL BUILDERS & CONSTRUCTION SUPPLY | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 81 | -10.83 |  | ON-GOING
|  | LARISIP-LARIS-034 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 3+926.00 - Sta. 5+528.00) of LARIS Lateral B, L = 1,571.00 m | 12408459 |  | 511 BUILDERS | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 80.3 | -11.53 |  | ON-GOING
|  | LARISIP-LARIS-035 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 5+528.00 - Sta. 6+575.00) of LARIS Lateral B, L = 935.00 m | 7541601 |  | R.M. VITUG CONSTRUCTION | 240 |  | 2020-03-09 | 2020-11-03 |  | 94.93 | 78.18 | -16.75 |  | ON-GOING
|  | LARISIP-LARIS-036 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 6+575.00 - Sta. 8+062.00) of LARIS Lateral B, L = 1,396.00 m | 11020930 |  | E.M. DANAN TRADING & CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 88.67 | 75.01 | -13.66 |  | ON-GOING
|  | LARISIP-LARIS-037 | Construction of Trapezoidal Concrete Canal Lining and Declogging of Structures (Sta. 8+062.00 - Sta. 9+368.00) of LARIS Lateral B, L = 1,264.50 m. | 10638578.4 |  | RONMARK CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 100 | 8.17 |  | COMPLETED / For Final Billing
|  | LARISIP-LARIS-038 | Construction of Trapezoidal Concrete Canal Lining (Sta. 9+368.00 - Sta. 9+720.00) and Rehabilitation ao Trapezoidal Concrete Canal Lining (Sta. 9+720.00 - Sta. 12+487.00) of LARIS Lateral B, L=2,922.00m | 4413458.34 |  | EDDMARI CONSTRUCTION AND TRADING | 210 |  | 2020-03-09 | 2020-10-04 |  | 100 | 100 | 0 |  | COMPLETED
|  | LARISIP-LARIS-039 | Construction of Trapezoidal Concrete Canal Lining (Sta. 1+654.00 - Sta. 2+520 and Sta. 4+682.00 - Sta. 4+950), Rehabilitation/Ugrading of Trapezoidal Concrete Canal Lining (Sta. 2+520.00 - Sta. 4+682.00) and Appurtenant Structures of LARIS Sub Lateral B-5, L=3,207.80 m. | 8300154 |  | KJRS CONSTRUCTION ENTERPRISES | 240 |  | 2020-03-09 | 2020-11-03 |  | 97.47 | 87.72 | -9.75 |  | ON-GOING
|  | LARISIP-LARIS-040 | Rehabilitation of Rectangular Concrete Canal Lining, Appurtenant Structure and Declogging of Structures (Sta. 0+000.00 - Sta. 6+747.00) of LARIS Sub Lateral B-7, L = 6,518.20m. | 8953793.9 |  | GVDPM CONSTRUCTION CORP. | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 39.94 | -51.89 |  | ON-GOING
|  | LARISIP-LARIS-041 | Hauling, Spreading and Compaction of Road Surfacing Materials (Sta. 0+742.00 - Sta. 1+536.00) & Construction of Rectangular Concrete Canal Lining (Sta. 1+536.00 - Sta. 1+850.00) of LARIS C and Construction of Rectangular Concrete Canal Lining (Sta. 0+953.00 - Sta. 2+227.00) of LARIS Lateral D, L = 2,317.00m. | 11279442.8 |  | ALCEL CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 87.2 | -4.63 |  | ON-GOING
|  | LARISIP-LARIS-042 | Construction of Rectangular Concrete Canal Lining (Sta. 2+311.00 - Sta. 3+487.00) of LARIS Lateral D, L = 1,155.00m. | 8484122 |  | IDI TRADING AND CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 78.67 | 90 | 11.33 |  | ON-GOING
|  | LARISIP-LARIS-043 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 0+000 - Sta. 0+659.50) of LARIS Lateral H, L = 647.00m. | 9322875.1 |  | GLF BUILDERS AND CONSTRUCTION SUPPLY | 270 |  | 2020-03-09 | 2020-12-03 |  | 83.67 | 95 | 11.33 |  | ON-GOING/ Substantially Completed
|  | LARISIP-LARIS-044 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structure (Sta. 0+659.50 - Sta. 1+442.00) of LARIS Lateral H, L = 750.00 m. | 9568145.7 |  | ALPHIN TRADING AND CONSTRUCTION | 270 |  | 2020-03-09 | 2020-12-03 |  | 90.2 | 81.46 | -8.74 |  | ON-GOING
|  | LARISIP-LARIS-045 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structure (Sta. 1+442.00 - Sta. 2+505.00) of LARIS Lateral H, L = 1,001.00m | 13226198.6 |  | W.J.P. CONSTRUCTION AND SUPPLY | 270 |  | 2020-03-09 | 2020-12-03 |  | 91.83 | 90 | -1.83 |  | ON-GOING
|  | LARISIP-LARIS-046 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 2+505.00 - Sta. 3+501.00) of LARIS Lateral H, L = 963.00m. | 11557680 |  | A.P. TAGARINO ENGINEERING AND CONSTRUCTION SERVICES | 270 |  | 2020-03-09 | 2020-12-03 |  | 83.67 | 90 | 6.33 |  | ON-GOING/ Substantially Completed
|  | LARISIP-LARIS-047 | Construction of Trapezoidal Concrete Canal Lining and Appurtenant Structures (Sta. 16+920.00 - Sta. 19+061.00) of LARIS Lateral B, L=2,141.00m. | 11991408 |  | RANIA CONSTRUCTION AND SUPPLIES | 270 |  | 2020-03-17 | 2020-12-11 |  | 81 | 27 | -54 |  | ON-GOING
|  | LARISIP-LARIS-048 | Construction of Trapezoidal Concrete Canal Lining and Appurtenant Structures (Sta. 0+000.00 - Sta. 0+480.00) of LARIS Sub-Lateral A-1, L=450.00m. | 3911280 |  | R.G. DIAZ BUILDERS & TRADING | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 34 | -66 |  | ON-GOING
|  | LARISIP-LARIS-049 | Construction of Trapezoidal Concrete Canal Lining and Appurtenant Structures (Sta. 0+480.00 - Sta. 1+258.60) of LARIS Sub-Lateral A-1, L=778.60m. | 4151231 |  | S.G. JUATCHON JR. CONSTRUCTION AND SUPPLIES | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 32 | -68 |  | ON-GOING
|  | LARISIP-LARIS-050 | Construction of Trapezoidal Concrete Canal Lining and Appurtenant Structures (Sta. 1+258.60 - Sta. 2+156.12) of LARIS Sub-Lateral A-1, L=892.60m. | 5357781 |  | J.S. LIM CONSTRUCTION & TRADING | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 57.63 | -42.37 |  | ON-GOING
|  | LARISIP-LARIS-051 | Construction of Trapezoidal Concrete Canal Lining (Sta. 2+156.12 - Sta. 3+043.00 and Sta. 3+205.50 - Sta. 3+369.00), Rectangular Concrete Canal Lining (Sta. 3+373.00 - Sta.3+862.00) and Appurtenant Structures of LARIS Sub-Lateral A-1, L=1,516.63m. | 11962592 |  | A.M.P. CONSTRUCTION | 270 |  | 2020-03-17 | 2020-12-11 |  | 90.5 | 40.04 | -50.46 |  | ON-GOING
|  | LARISIP-LARIS-052 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 3+862.00 - Sta. 5+260.00) of LARIS Sub Lateral A-1, L= 1,398.00m. | 11793905 |  | A.M.P. CONSTRUCTION | 270 |  | 2020-03-17 | 2020-12-11 |  | 90.5 | 51.26 | -39.24 |  | ON-GOING
|  | LARISIP-LARIS-053 | Rehabilitation/Upgrading of Trapezoidal Concrete Canal Lining (Sta. 0+000.00 - Sta. 0+812.00), Construction of Trapezoidal Concrete Canal Lining (Sta. 0+823.00 - Sta. 1+654.00) & Appurtenant Structures of LARIS Sub-Lateral B-5 and Rehabilitation of Rectangular Concrete Canal Lining (Sta. 0+000.00 - Sta. 3+230.50), Construction of Rectangular Concrete Canal Lining (Sta. 3+230.50 - Sta. 3+565.00) & Declogging of Structures of LARIS Sub-Lateral B-6, L=5,082.50m. | 7398644 |  | MAÑALAC CONSTRUCTION AND SUPPLY | 240 |  | 2020-03-17 | 2020-11-11 |  | 95.5 | 75 | -20.5 |  | ON-GOING
|  | LARISIP-LARIS-054 | Rehabilitation of Trapezoidal Concrete Canal Lining (Sta. 8+758.00 - Sta. 16+380.00) of LARIS Lateral E, L=7,400.00m. and Rehabilitation of Rectangular Concrete Canal Lining (Sta. 0+000.00 - Sta. 1+756.00) of LARIS Lateral B-3b, L=1,756.00m. | 6009337 |  | J.S. LIM CONSTRUCTION & TRADING | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 89.07 | -10.93 |  | ON-GOING
|  | LARISIP-LARIS-055 | Construction of Trapezoidal Concrete Canal Lining(Sta. 8+294.00 - Sta. 8+758.00) of LARIS Lateral E, L=449.00m. | 4123130 |  | R.G. TABIN CONSTRUCTION & SUPPLY | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 100 | 0 |  | COMPLETED
|  | LARISIP-LARIS-056 | Construction of Trapezoidal Concrete Canal Lining(Sta. 7+732.00 - Sta. 8+294.00) of LARIS Lateral E, L=562.00m. | 5306289 |  | MAÑALAC CONSTRUCTION AND SUPPLY | 210 |  | 2020-03-17 | 2020-10-12 |  | 100 | 100 | 0 |  | COMPLETED
|  | LARISIP-LARIS-057 | Construction of Closed Conduit (Sta. 4+230.00 - Sta. 4+280.60) of LARIS Lateral E and Upgrading of Rectangular Concrete Canal Lining (Sta. 0+000.00 - Sta. 0+960.00 & Sta. 1+643.00 - Sta. 1+996.00), Construction of Rectangular Concrete Canal Lining (Sta. 0+960.00 - Sta. 1+643.00) & Thresher Crossing (Sta. 1+440.00) of LARIS Lateral E-1, L=2,018.15m. | 8466787 |  | J-THREE BAGWIS CONSTRUCTION COMPANY | 270 |  | 2020-03-17 | 2020-12-11 |  | 81.5 | 50.08 | -31.42 |  | ON-GOING
|  | LARISIP-LARIS-058 | Construction of Rectangular Concrete Canal Lining (Sta.1+996-Sta. 2+000) and Sta. 2+052-Sta. 3+753.50,Upgrading of Rectangular Concrete Canal Lining (Sta. 2+000-Sta. 2+052) and Appurtenant Structures of LARIS Lateral E-1 , L=1695.45m | 12050265 |  | A.M.P. CONSTRUCTION | 270 |  | 2020-03-17 | 2020-12-11 |  | 90.5 | 89.5 | -1 |  | ON-GOING
|  | LARISIP-LARIS-059 | Construction of Rectangular Concrete Canal Lining (Sta. 3+753.50 - Sta. 4+440.00) and Drop Structure (Sta. 4+420.00) of LARIS Lateral E-1, L=658.35m. | 7029044 |  | MCB CONSTRUCTION AND SUPPLY | 240 |  | 2020-03-17 | 2020-11-11 |  | 67.95 | 90 | 22.05 |  | ON-GOING/ Substantially Completed
|  | LARISIP-LARIS-060 | Modification of Structures with Fabrication, Supply, Delivery and Installation Supervision of Steel Gates of LARIS Main Canal and Lateral B | 2850994 |  | VYRAGUS CONSTRUCTION | 180 |  | 2020-06-09 | 2020-12-05 |  | 79.7 | 80 | 0.3 |  | ON-GOING
|  | LARISIP-LARIS-061 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 3+501 - Sta. 4+260) of LARIS Lateral H | 6955782.33 |  | G.G. UY CONSTRUCTION | 210 |  | 2020-06-16 | 2021-01-11 |  | 27.33 | 70 | 42.67 |  | ON-GOING
|  | LARISIP-LARIS-062 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 4+260 - Sta. 5+266.05) of LARIS Lateral H | 8502839 |  | Z-5 CONSTRUCTION CORPORATION | 270 |  | 2020-06-16 | 2021-03-12 |  | 51 | 95 | 44 |  | ON-GOING/ Substantially Completed
|  | LARISIP-LARIS-063 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 5+266.05 - Sta. 6+440) of LARIS Lateral H | 10136494 |  | SYNDTITE CONSTRUCTION CORPORATION | 270 |  | 2020-06-16 | 2020-07-07 |  | 51.07 | 95 | 43.93 |  | ON-GOING
|  | LARISIP-LARIS-064 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 0+000 - Sta. 2+089) of LARIS Sub-Lateral D-1 Extra | 4266532 |  | AMVIL CONSTRUCTION & SUPPLIES | 210 |  | 2020-06-16 | 2021-01-11 |  | 25.13 | 55.11 | 29.98 |  | ON-GOING
|  | LARISIP-LARIS-065 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 0+000 - Sta. 1+484) of LARIS Sub-Lateral D-2 | 3109349.5 |  | PAS CONSTRUCTION & SUPPLIES | 180 |  | 2020-06-16 | 2020-12-12 |  | 66.33 | 61.63 | -4.7 |  | ON-GOING
|  | LARISIP-LARIS-066 | Construction of Rectangular Concrete Canal Lining and Appurtenant Structures (Sta. 0+000 - Sta. 1+650) of LARIS Sub-Lateral D-3 | 4936573 |  | F.A. ASPRER CONSTRUCTION | 210 |  | 2020-06-16 | 2021-01-11 |  | 32 | 35 | 3 |  | ON-GOING
|  | LARISIP-ADRIS-012 | Construction of Thresher Crossing with Check (Sta. 1+469), Turnout (Sta. 1+455 Left Side) and Wasteway (Sta. 1+455 Right Side) of ADRIS Lateral O | 1684622 |  | KJRS CONSTRUCTION ENTERPRISES | 180 |  | 2020-06-16 | 2020-12-12 |  | 71 | 95 | 24 |  | ON-GOING/ Substantially Completed
|  | LARISIP-LARIS-067 | Construction of Trapezoidal Concrete Canal Lining (Sta. 9+998 - Sta. 10+545) of LARIS Lateral E | 4633124 |  | MN COLOMA CONSTRUCTION | 150 |  | 2020-08-25 | 2021-01-21 |  | 41 | 70 | 29 |  | ON-GOING
|  | LARISIP-LARIS-068 | Construction of Rectangular Concrete Canal Lining (Sta. 5+640 - Sta. 6+141) of LARIS Lateral CD-1-6 | 6649464 |  | MAÑALAC CONSTRUCTION AND SUPPLY | 150 |  | 2020-08-25 | 2021-01-21 |  | 26 | 21.02 | -4.98 |  | ON-GOING
|  | LARISIP-ADRIS-013 | Construction of Drain Inlet (Sta. 27+590) of ADRIS Main Canal | 4843856 |  | GLF BUILDERS AND CONSTRUCTION SUPPLY | 150 |  | 2021-08-25 | 2021-01-21 |  | 39.67 | 43.56 | 3.89 |  | ON-GOING
Sulvec Small Reservoir Irrigation Project
|  | Sulvec SRIP Package 1 | Service Road Works | 14134795.56 |  | Remar Construction | 365 |  | 2020-05-18 | 2021-05-19 |  | 35.26 | 98.49 | 63.23 |  | On-going
|  | Sulvec SRIP Package 2 | Protection Works | 4517042.21 |  | Amstek Construction | 270 |  | 2020-05-20 | 2021-02-15 |  | 29.37 | 90.83 | 61.46 |  | On-going
|  | Sulvec SRIP Package 3 | Canal Lining | 14113937.97 |  | Remar Construction | 365 |  | 2020-05-18 | 2021-05-19 |  | 42.56 | 49.23 | 6.67 |  | On-going
|  | Sulvec SRIP Package 4 | Canal Structure & Drainage System | 5575985 |  | MSF Construction | 270 |  | 2020-05-20 | 2021-02-15 |  | 42.53 | 36.65 | -5.88 |  | On-going
REGION 3
Balog-Balog Multipurpose Project-Phase II
|  | Improvement of Service Road along Lateral B-2 | Improvement of Service Road along Lateral B-2, LMC-BBMPII-020-03 | 8003047.3 |  | Malta Construction & Supply | 99 |  | 2020-07-03 | 2020-10-09 |  | 100 | 100 | 0 |  | completed on September 30, 2020
|  | Spurdikes on Moriones Riverbank | Spurdikes on Moriones Riverbank, LMC-BBMPII-20-NP-04 | 14446635.18 |  | BMNY Construction and Enterprises | 60 |  | 2020-06-22 | 2020-08-20 |  | 100 | 100 | 0 |  | Completed on July 30, 2020
|  | Slope Protection and Restoration Works, Northern Area | Slope Protection and Restoration Works, Northern Area, LMC-BBMPII-NP-20-03 | 1492216.89 |  | Vyragus Construction | 30 |  | 2020-07-22 | 2020-07-31 |  | 100 | 100 | 0 |  | Completed on July 21, 2020
|  | Embankment Construction and Construction and Slope Protection Works for Tarlac Diversion Dam Ogee No. 2 | Embankment Construction and Construction and Slope Protection Works for Tarlac Diversion Dam Ogee No. 2, LMC-BBMPII-NP-20-05 | 23045371.68 |  | Syndtite Construction Corp. | 70 |  | 2020-08-17 | 2020-10-25 |  | 100 |  | -100
UPRIIS
Marikit Irrigation Project
|  | Construction of Main Canal (Sta. 1+045 - Sta. 2+500) and Related Structures | Marikit Irrigation Project Phase 4 | 14507941.7 |  | GTY Construction | 240 |  | 2020-03-18 | 2020-11-12 |  | 25.59 | 22.29 | -3.3 |  | On-going
REGION 7
Bonot-Bonot Small Reservoir Irrigation Project
|  | Bonotbonot SRIP | Const. of Lined Canals, Canal Structures, and Fab. & Installation of Steelgates | 8304534.46 |  | HERMCOR Const. & Supply | 210 |  | 2020-07-03 | 2021-01-29 |  | 100 |  | -100
REGION 8
Bugko Irrigation Project
|  | Bugko IP 01-2020 | Repair of Dam (completion), Construction of Canal and Canal Structures | 46227142.57 |  | SAL CONSTRUCTION | 500 |  | 2020-03-16 | 2021-07-28 |  | 23.97 | 19.56 | -4.41 |  | On-going
Catarman-Bobon Irrigation Project
|  | Catarman-Bobon IP #01- 2020 | Construction of Concrete Canals and Canal Structures | 19477171.64 |  | SOLID M Construction | 270 |  | 2020-03-20 | 2020-11-21 |  | 69.91 | 61.8 | -8.11 |  | Suspended
REGION 9
Lower Sibuguey I River Irrigation System Extension Project
|  | Lower Sibuguey I RIS Extension Project |  | 35584586.29 |  | F.A Torres Costruction | 352 |  | 2020-05-29 | 2021-02-22 |  | 10 | 39.12 | 29.12 |  | Ongoing delivery of embankment materials for the preparation of the HDPE installation. Slow progress due to successive heavy rains that makes the access road unpassable
REGION 11
Upper Saug River Irrigation Project
|  | LMC No. 2020-11 | Completion of Diversion Dam, Concrete Lining of Main Canal, Lateral E, Lateral G and Lateral F, Protection Works of Main Canal (Supply, Delivery, Installation and Maintenance of Coconet and Vetiver); Furnish, Delivery, and Installation of 19 Units Steel Gates | 85996865.14 |  | GP & H CONSTRUCTION, INC. | 300 |  | 2020-06-30 | 2021-05-03 |  | 29 | 18.74 | -10.26 |  | Construction on-going.
REGION 12
Malitubog-Maridagao Irrigation Project Phase II
|  | LMC-021, Package 1 | Construction of RMC2, Station 11+460 - 12+540 (1.080) | 93476738.22 |  | Hervelyn Intertrading and Builders Corp. | 270 |  | 2020-05-28 | 2021-05-02 |  | 37.03 | 1.01 | -36.02 |  | Ongoing
|  | LMC-021, Package 2 | Construction of lateral D, station 0+000 - 1+080 & lateral D1, station 0+000 - 0+600 (1.680 km) | 73293879.26 |  | Sunstone Construction and Supply | 240 |  | 2020-05-29 | 2021-01-24 |  | 8.65 | 0.5 | -8.15 |  | Ongoing
|  | LMC-021, Package 3 | Lateral D, station 1+080 - 2+660 & lateral D2, station 0+000 - 1+009 (2.589 km) | 72258469.41 |  | Monolithic Construction & Supply | 240 |  | 2020-06-01 | 2021-01-27 |  | 13.71 | 0.5 | -13.21 |  | Ongoing
|  | LMC-021, Package 4 | Lateral D, station 2+660 - 5+498.21 & Lateral D3, station 0+000 - 1+360 (4.198) | 73676344.26 |  | Sunstone Construction and Supply | 240 |  | 2020-05-29 | 2021-01-24 |  | 8.64 | 0.5 | -8.14 |  | Ongoing
REGION 13
Bislig City Integrated Development Project-Irrigation Component
|  | LMC-2020-BCIDP-IC-01-RO | CANALIZATION, CANAL STRUCTURES & TERMINAL FACILITIES | 51174747.9 |  | ARQ BUILDERS | 300 |  | 2020-05-22 | 2021-03-18 |  | 30 | 25 | -5 |  | No activity @ project site due to covid local transmission resulting to substantial decrease of manpower